## Sheet1
Story ID | Story Name | As a/an | I want… | so that… | Priority | Iteration No. | Acceptance Criteria | Notes | Date started | Date finished
1 | Electricity consumption and cost view | Consumer | to have a look of the live electricity usage and cost of the day. | I can know how much electricity I have used and the cost during the day. | 1 | 1 | 1. Verify that it can list the live electricity usage and cost of the day. 2. Verify that it can update the electricity usage and cost of the day frequently. | Usage in kWh. Cost = usage * unit price, in ￡. | 2018-04-23 | 2018-05-12
2 | Gas consumption and cost view | Consumer | to have a look of the live gas usage and cost of the day. | I can know how much gas I have used and the cost during the day. | 1 | 1 | 1. Verify that it can list the live gas usage and cost of the day. 2. Verify that it can update the gas usage and cost of the day frequently. | Usage in kWh. Cost = usage * unit price, in ￡. | 2018-04-23 | 2018-05-12
3 | Set Budget | Consumer | to control energy cost in a certain range. | this software will set a budgetary gradient and user-defined that users can choose. | 1 | 1 | 1. Verify that there are two kinds of patterns: the cost that the system provided and user-defined cost 2. Verify that budget of each family will be sent to the administrator | Budget in ￡. | 2018-04-23 | 2018-05-12
4 | Alarm | Consumer | to be reminded when the budget when the cost exceeds the budget. | the software will send a budget alarm when the cost exceeds the budget that use decide. | 1 | 1 | 1. Verify that alarm should be sent to user in time 2. Verify that alarm has the rank what is decided by the number of exceed budget. 3. Verify that users can close the alarm. | Alarm level in ￡. | 2018-04-23 | 2018-05-15
5 | Historic comsumption view | Consumer | to have a list of electricity and gas comsumption of every month, week or day. | I can know how much electricity or gas I have used during any period. | 2 | 1 | 1. Verify that it can list the consumption by month or day according to the choice of the user. 2. Verify that daily, weekly and monthly electricity or gas usage are saved in the list. 3. Verify that the lists should be updated frequently. | Usages in kWh. | 2018-04-30 | 2018-05-15
6 | Historic cost view | Consumer | to have a list of electricity and gas cost of every month, week or day. | I can know how much I paid for the electricity or gas during any period. | 2 | 1 | 1. Verify that it can list the cost by month or day according to the choice of the user. 2. Verify that daily, weekly and monthly electricity or gas cost are saved in the list. 3. Verify that the changings of tariff will not affect the correctness of the daily, weekly or monthly cost. 4. Verify that the lists should be updated frequently. | Cost = Usage * Tariff, in ￡. | 2018-04-30 | 2018-05-15
7 | Check tariff | Consumer | to check the tariffs of gas and electricity at any time, the number should be easy to read. | I can determine the consumption on gas and electricity to save money. | 2 | 1 | 1. Verify that make sure there is a button on Household Smart energy monitoring software, when user press it, the current tariffs of electricity and gas would be shown. 2. Verify that the unit of the output should be in ￡/kWh. 3. Verify that the user can only read the value of tariffs rather than write it. 4. Verify that the user cannot check the history of tariffs with this button. | Tariff in GBP per unit usage, ￡/kWh. | 2018-04-30 | 2018-05-15
8 | Send meter reading to energy provider | Consumer | the Household Smart energy monitoring software can send the meter readings of electricity and gas automatically | I don't need to spend my time on doing so. | 3 | 1 | 1. Verify that the meter readings of electricity and gas would be sent to energy provider automatically on every first day in a month. 2. Verify that the unit of the readings should be in kWh as four-digit number. | Usage in kWh. Cost = usage * unit price, in ￡. | 2018-05-07 | 2018-05-19
9 | User information modification | Energy probider | to add new consumer and meter information. | the capacity of consumer will be expanded, the company make more profit. | 4 | 1 | Verify that the provider can find the newly added consumer or meter information. | N/A | 2018-05-14 | 2018-05-21
10 | User information modification | Energy probider | to view existing consumer and meter information. | the consumption record with the background of the consumer can be storaged in order to provide better service. | 4 | 1 | Verify that the list of the specific consumer and meter information can be clearly presented. | N/A | 2018-05-14 | 2018-05-21
11 | User information modification | Energy probider | to remove existing consumer and meter information. | the invalid or ineffective information can be erased to preserve the company's database. | 4 | 1 | Verify that the removed item cannot be searched in the list of all the consumer and meter information. | N/A | 2018-05-14 | 2018-05-21
12 | Tariff setup | Energy probider | to set the current traiff. | guarantee the profit of the company. | 3 | 1 | Verify that the new tariff can be checked by consumers. | Tariff in GBP per unit usage, ￡/kWh. | 2018-05-07 | 2018-05-19
13 | Meter readings receive | Energy probider | to acquire the readings of each household. | the reading of household meter is collected accurately to prevent commercial dispute. | 3 | 1 | Verify that the reading of the meter is identical to the reading on consumer's household meter. | Usage in kWh. Cost = usage * unit price, in ￡. | 2018-05-07 | 2018-05-19
14 | Bill generation | Energy probider | to generate the bill and send the bill to the customer | make sure the revenue of the company. | 5 | 1 | Verify that the users can successfully receive the complete bill through either email or traditional mailbox. | Usage in kWh. Cost = usage * unit price, in ￡. | 2018-05-14 | 2018-05-25
Priority from 1 to 5, corresponding from most urgent to least urgent